## Advanced Planning
Program Advanced Planning
Date
Task | Committee | Assignee | Assistant | Due Date | Status
.

## Sample
Olam Tikvah Shomrei Ha'aretz
Date 2011-2012 (2011 activites duplicated in 2012)
Task | Committee | Assignee | Assistant | Due Date | Status
Coordinate date with farm owner and synagogue | Executive | Eric | Pablo | 2011-06-15 | Done
Submit announcement to August OT Monthly Pub | Communications | Bob |  | 2011-06-28 | Done
Plan Event with Rabbi | Social Action | Eric |  | 2011-08-01 | Done
Submit announcement to September OT Monthly Pub | Communications | Bob |  | 2011-07-28 | Done
Place announcements in Shabbat Bulletin | Communications | Bob |  | 8/2011-9/2011 | Done
Update website | Communications | Bob |  | 2011-08-01 | Done
Collect RSVPs | Social Action | Eric |  | 2011-09-23 | Done
Send information on logistics to participants | Social Action | Eric |  | 2011-09-21 | Done
Recruit Photographer |  | Eric |  | 2011-09-18 | Done
Deliver food to food bank | Social Action | Eric | Pablo | 2011-09-25 | Done