## Explanation
Torch Award Program Schedule
On the online application, we ask that you describe the timeline with all the tasks to make the program work. The timeline will explain: aspects of program advance planning, how long did it take, key events, how did your members participate. Describe this information on a spreadsheet such as the ones that follow and upload it to the online application.

## Timeline
Cantorial Program Schedule
for 5/17/2020
Task | Assignee | Due Date | Status
Reach out to other Shul clubs | Seth | 2020-03-18 | Done
Finalize clubs that will participate | Seth | 2020-03-30 | Done
Planning meeting with club reps to discuss logistics | Seth, Andrew, Alan,Steve | 2020-04-02 | Done
Reach out to clergy to solidify particiaption | Each club rep to reach out to their own clergy | 2020-04-15 | Done
Initial Planning Meeting with Clergy Performers | Seth, Andrew, Alan,Steve, and clergies | 2020-04-23 | Done
Solidify Date and time for concert | Seth and Mark | 2020-04-29 | Done
Set up Eventbrite annd bitly | Matthew | 2020-04-30 | Done
Flyer | Seth | 2020-05-05 | Done
Publicity out to congregations | Seth, Andrew, Alan,Steve, and clergies | 2020-05-10 | Done
Finalize concert format and song selections performers | Seth, Andrew, Alan,Steve and clergy performers | 2020-05-10 | Done
Program | Seth | 2020-05-11 | Done
Zoom settings with performers | Matthew and clergy performers | 2020-05-13 | Done
Send Zoom info out to attendees | Matthew | 5/15202 | Done
Concert | All | 5/172020 | Done