## Advanced Planning
Program Advanced Planning
Date
Task | Committee | Assignee | Assistant | Due Date | Status
.

## Sample
Roots in Israel Program Advanced Planning
Date: March 14, 2013
Task | Committee | Assignee | Assistant | Due Date | Status
Roots in Israel idea founded | Ad hoc | David Greenfield, Dennis Buchenholz, Danny Mandau | David Beckman | May 2011 | Done
Roots in Israel Brotherhood committee formed | Roots | David Greenfield | Dennis B. | June 2011 | Done
Pitch program to Brotherhood | Roots | David Greenfield | Dennis B., Danny M. | Sept 2011 | Done
Initial Funding approved by Brotherhood | Brotherhood | David Greenfield | Dennis B., Danny M. | Dec 2011 | Done
Solidify partnership with JNF | Roots | Dennis B. | David G. | April 2012 | Done
Yom Ha'atzmaut collection day, temple wide, for languishing existing pushkies | Roots | David Greenfield | Danny M. | 2012-04-28 | Done
Finalize program logo, sticker for JNF blue box, business cards for PR | Roots | David Greenfield | Dennis B. | 2012-07-27 | Done
Create list of weekly facts on Israel | Roots | Dennis B. | Danny M. | 2012-08-13 | Done
Create Roots in Israel website on temple website in Brotherhood section | Roots | Brian Lefsky | David G. | 2012-09-05 | Done
Official launch of program at temple wide BBQ | Roots | David Greenfield | Dennis B. | 2012-09-09 | Done
Tie in weekly publicity for weekly facts on Israel to temple weekly electronic mailing | Roots | Brian Lefsky | Danny M. | 2012-09-12 | Done
Install sticker, pack JNF pushkies with cover letter for delivery to all temple members | Roots | Dennis B. | David G. | 2012-10-15 | Done
First official collection week for JNF boxes, Tu B'Shevat | Roots | David Greenfield | Danny M. | 2013-01-27 | Done
Work with Boston Globe to publish article on Roots in Israel program | Roots | David Greenfield | Al Kaplan | 2013-02-24 | Done
Second official collection week for JNF boxes, Yom Ha'atzmaut | Roots | David Greenfield | Danny M. | 2013-04-28
Roots program to be featured in the May edition of the newly formatted temple bulletin | Roots | David Greenfield |  | May 2013
Roots booth at temple wide BBQ, continued PR | Roots | David Greenfield | Danny M. | 2013-09-22
On going update to website for personal stories from people who visited Israel | Roots | Brian Lefsky | David G. | on going
On going coordination with temple photo corps to have photos taken at all events | Photo Corps | Al Kaplan | David G. | on going
Periodic outreach to congregation on Roots activities through te-talk (informal e-mail communication) | Roots | David Greenfield |  | on going
Monthly update on Roots program at monthly Brotherhood meeting | Roots | David Greenfield | Dennis B. | on going