## Sample 1
Torch Award Program Schedule |  |  | (Sample items inserted)
As of Date
2020-10-05
Task |  | Assignee | Assistant | Due Date | Status
Planning
Reach out to Rabbi Abraham to invite to Men's Club Meetings |  | Kevin |  | 2020-08-18 | Done
Ask Rabbi about introduction/event presentation |  | Kevin | Scot | 2020-08-19 | Done
Ask Building Committee about shul/sukkah usage during pandemic | Finance | Kevin | Scot | 2020-09-09 | Done
Reach out to Web Registration Designer for RSVP form |  | Kevin |  | 2020-09-22 | Done
Publicity
Update website |  | Tanya |  | 2020-09-22 | Done
Email Men's Club leadership |  | Kevin | Scot | 2020-09-23 | Done
Execution
Sukkah Set up |  | Octavio |  | 2020-10-03 | Done
Welcome speaker |  | Kevin |  | 2020-10-03 | Done
Welcome attendees |  | Kevin | Scot | 2020-10-03 | Done
Presentation |  | Rabbi Abraham | All | 2020-10-03 | Done