## Advanced Planning
Program Advanced Planning
Date
Task | Committee | Assignee | Assistant | Due Date | Status
.

## Sample
Program Advanced Planning: 8th Annual Sukkahfest - Beef & Beer In the Sukkah
Date | Description
May | Secure date for Succahfest in the Sukkah with the Temple's Executive Dirctor Programming Director and put on both Temple and Men's Club calendar of events.
June | Identify theme for Sukkahfest
July | Research craft beers and determine which are considered kosher.
July | Work with local liquor store owner to identify brewery to reach out to for individual to give presentation on recommended kosher craft beers.
July | Complete program flyer and submit to Temple for internal publicity.
July | Submit online publicity form to Temple's marketing director with program details for internal publicity.
August | Send e-blast to Men's Club members with upcoming programs.
August / Sept. | Assemble team of Men's Club volunteers to handle day of event activities: pick up all food/drinks and supplies, handle registration, verify room logistics, barbecue and serve food, etc.
September | Temple-wide publicity: announcement of program on Shabbat leaflets, program flyer around shul, standalone e-blasts about program, inclusion in weekly program announcements.
1 week prior to program | Send e-blast to prior attendees who have not yet RSVP'd reminding them about the program and encouraging them to attend again.
3 days prior to program | Expected number of attendees based on RSVPs to date and anticipated walk-ins. Communicate to kosher market handling event.
3 days prior to program | Submit room function form - Set-up for seating (tables + chairs), registration table, and tables for food and drinks, podium/mic if needed, and any audio-visual needs -TV, screen, projector, laptop, etc.
3 days prior to program | Verify needs: food, drinks, paper goods
3 days prior to program | Confirm with contact at brewery the arrangements for the presentation and tasting of the kosher craft beers
Shortly after program | Submit photos to Temple marketing director and newsletter editor for possible inclusion in various social media and print outlets.
Shortly after program | Work with Treasurer and Assistant Treasurer in determining all program revenues and expenses.