## Advanced Planning
Program Advanced Planning
Date
Task | Committee | Assignee | Assistant | Due Date | Status
Contact Pino's for wine discount | Fundraising Committee - High Holiday Cake-Challah-Wine Sale | Ray Sabin | Craig Artel | 2012-07-15 | Completed
Contact Mordy's Bakery and get prices | Fundraising Committee - High Holiday Cake-Challah-Wine Sale | Ray Sabin | Craig Artel | 2012-07-25 | Completed
Draft price list and order form submit to office for publication | Fundraising Committee - High Holiday Cake-Challah-Wine Sale | Ray Sabin | Craig Artel | 2012-08-01 | Completed
Submit column for Kiruv - September/October issue | Publicity | Craig Artel | Nate Kean | 2012-08-01 | Completed
Submit ad copy to office for publication in Kiruv, temple weekly phone blasts and bimah announcements; send e-blast with order forms to listserv, and add order forms to Facebook/Twitter prior to sale, and repeat as needed in days prior to sale | Publicity - High Holiday Cake-Challah-Wine Sale | Ray Sabin | Craig Artel | 2012-08-22 | Completed
Arrange for delivery and volunteers for distribution | Fundraising Committee - High Holiday Cake-Challah-Wine Sale | Ray Sabin | Craig Artel | 2012-09-06 | Competed
Order steaks from supplier | Dinner Committee - Steak & Scotch | Al Davis | Nate Kean | 2012-09-16 | Completed
Contract with Morrell for 6 scotches | Dinner Committee - Steak & Scotch | Marty Golden | Nate Kean | 2012-09-16 | Completed
Submit flyer ad copy to office for mailings, publication in Kiruv, temple weekly phone blasts and bimah announcements; send e-blast with flyer to listserv; add event registration to Facebook and repeat as needed in days prior to event | Publicity - Steak & Scotch | Craig Artel | Nate Kean | 2012-09-16 | Completed
Supermarket run for all supplies and ingredients | Dinner Committee - Steak & Scotch | Marc Weinstein, Marty Golden | Nate Kean | 2012-10-01 | Completed
Submit column for Kiruv - November/December issue | Publicity | Craig Artel | Nate Kean | 2012-10-01 | Completed
Submit ad copy to office for publication in Kiruv, temple weekly phone blasts and bimah announcements | Breakfast/Speaker Committee - Hearing Men's Voices | Al Davis | Ray Sabin | 2012-10-14 | Completed
Select Man/Youth of the Year | Man of the Year | Executive Board |  | 2012-10-01 | Completed
Select Chairman for reservations, ad journal | Man of the Year | Craig Artel | Ray Sabin | 2012-10-01 | Completed
Submit flyer ad copy to office for mailings, publication in Kiruv, temple weekly phone blasts and bimah announcements; send e-blast with flyer to listserv; add event registration to Facebook and repeat as needed in days prior to event | Man of the Year | Craig Artel | Ray Sabin | 2012-10-22 | Completed
Select comedian | Dinner Committee - December 24th Show | Nate Kean | Jay Culang | 2012-10-01 | Completed
Submit column for Kiruv - January/February issue | Publicity | Craig Artel | Nate Kean | 2012-12-01 | Completed
Contract with Avi - details | Dinner Committee - December 24th Show | Nate Kean | Jay Culang | 2012-10-01 | Completed
Contract with caterer - select menu | Dinner Committee - December 24th Show | Marty Golden | Larry Klioze, Phil Schmidt | 2012-11-01 | Completed
Submit flyer ad copy to New Jersey Jewish News, Northern New Jersey Region; temple office for mailings, publication in Kiruv, temple weekly phone blasts and bimah announcements; send e-blast with flyer to listserv; add event registration to Facebook and repeat as needed in days prior to event | Publicity - December 24th Show | Ray Sabin | Craig Artel | 2012-11-15 | Completed
Finalize contract with caterer - headcount, amount of food | Dinner Committee - December 24th Show | Marty Golden | Nate Kean | 2012-11-25 | Completed
Finalize contract with NJ Blood Services, reserve Tabak Hall | Blood drive | Jerry Langer | Linda Schmidt | 2012-11-21 | Completed
Submit flyer ad copy to New Jersey Jewish News, Northern New Jersey Region; temple office for mailings, publication in Kiruv, temple weekly phone blasts and bimah announcements; send e-blast with flyer to listserv; add event registration to Facebook and repeat as needed in days prior to event | Publicity - Blood drive | Craig Artel | Jerry Langer | 2013-01-04 | Completed
Submit flyer ad copy to temple office for mailings, publication in Kiruv, temple weekly phone blasts and bimah announcements; send e-blast with flyer to listserv; add event registration to Facebook and repeat as needed in days prior to event | Publicity - Chili Cookoff | Craig Artel | Marc Weinstein | 2013-01-05 | Completed
Secure teams for registration | Dinner Committee - Chili Cookoff | Marc Weinstein | Bruce Herniter | 2013-01-16 | Completed
Collect ingredient lists and supermarket run | Dinner Committee - Chili Cookoff | Marc Weinstein | Bruce Herniter | 2013-01-23 | Completed
Reserve kitchen for cooks | Dinner Committee - Chili Cookoff | Marc Weinstein | Bruce Herniter | 2013-01-23 | Completed
Reserve speaker | Breakfast/Speaker Committee - World Wide Wrap | Craig Artel | Al Davis | 2012-06-05 | Completed
Submit column for Kiruv - March/April issue | Publicity | Craig Artel | Nate Kean | 2013-02-01 | Completed
Submit flyer ad copy to temple office for mailings, publication in Kiruv, temple weekly phone blasts and bimah announcements; send e-blast with flyer to listserv; add event registration to Facebook and repeat as needed in days prior to event | Publicity - World Wide Wrap | Craig Artel | Al Davis | 2012-10-15 | Completed
Confer with Education Committee for new date | Breakfast/Speaker Committee - Freedman | Ray Sabin | Steve Parkoff | 2013-01-15 | Completed
Submit flyer ad copy to New Jersey Jewish News, Northern New Jersey Region; temple office for mailings, publication in Kiruv, temple weekly phone blasts and bimah announcements; send e-blast with flyer to listserv; add event registration to Facebook and repeat as needed in days prior to event | Breakfast/Speaker Committee - Freedman | Ray Sabin | Craig Artel | 2013-01-15 | Completed
Contact bakery for breakfast (bagels, etc), headcount | Breakfast/Speaker Committee - Freedman | Ray Sabin | Marty Golden | 2013-02-08 | Completed
Coordinate with Religious Committee; secure Torah leyners, aliyot, bimah honors, ushers, volunteers for leading services, dvrei Torah, speeches, etc. | Men's Club Shabbat | Nate Kean | Al Davis | 2013-02-22 | Completed
Coordinate with temple office for catering of kiddush | Men's Club Shabbat | Craig Artel | Marty Golden | 2013-03-01 | Completed
Submit flyer ad copy to New Jersey Jewish News, Northern New Jersey Region; temple office for mailings, publication in Kiruv, temple weekly phone blasts and bimah announcements; send e-blast with flyer to listserv; add event registration to Facebook and repeat as needed in days prior to event | Shamsky breakfast | Craig Artel | Ray Sabin | 2013-03-01 | Completed
Contact bakery for breakfast (bagels, etc), headcount | Shamsky breakfast | Ray Sabin | Marty Golden | 2013-03-14 | Completed
Contact Pino's for wine list | Fundraising Committee - Pesach Cake-Wine Sale | Craig Artel | Ray Sabin | 2013-02-15 | Completed
Contact Butterflake for price list discount, order forms | Fundraising Committee - Pesach Cake-Wine Sale | Marty Golden | Craig Artel | 2013-02-15 | Completed
Draft price list and order form submit to office for publication | Fundraising Committee - Pesach Cake-Wine Sale | Marty Golden | Craig Artel | 2013-02-15 | Completed
Submit ad copy to office for publication in Kiruv, temple weekly phone blasts and bimah announcements; send e-blast with order forms to listserv, and add order forms to Facebook/Twitter prior to sale, and repeat as needed in days prior to sale | Publicitiy - Pesach Cake-Wine Sale | Craig Artel | Ray Sabin | 2013-02-22 | Completed
Arrange for delivery and volunteers for distribution | Fundraising Committee - Pesach Cake-Wine Sale | Ray Sabin | Craig Artel | 2013-03-18 | Completed
Submit column for Kiruv - May issue | Publicity | Craig Artel | Nate Kean | 2013-04-01 | Completed
Get shaloch manot delivery list from Sisterhood, divide into routes | Yellow Candle | Marc Weinstein | Albert Mitzner | 2013-02-25 | Completed
Secure volunteers for bagging candles | Yellow Candle | Nate Kean | Marc Weinstein | 2013-03-10 | Completed
Secure volunteers for delivery | Yellow Candle | Nate Kean | Marc Weinstein | 2013-03-17 | Completed
Submit ad copy to office for publication in Kiruv, temple weekly phone blasts and bimah announcements; send e-blast with letter to listserv, post on Facebook/Twitter and repeat as needed in days prior to Yom HaShoah | Yellow Candle | Craig Artel | Marc Weinstein | 2013-03-31 | Completed
Deliver candles on all 20+ routes | Yellow Candle | Marc Weinstein | various | 2013-04-07 | Completed
Secure participants | Activities - Laser Tag | Julie Katz | Asher Weinstein | 2013-04-15 | Completed
Send e-blast with letter to listserv, post on Facebook/Twitter and repeat as needed in days prior to event | Publicity - Laser Tag | Julie Katz | Asher Weinstein | 2013-04-15 | Completed
Secure participants to register for run | Activities - Rutgers Hillel 5K | Al Davis | Craig Artel | 2013-04-01 | Completed
Send e-blast with letter to listserv, post on Facebook/Twitter and repeat as needed in days prior to event | Activities - Rutgers Hillel 5K | Craig Artel | Al Davis | 2013-04-01 | Completed
Finalize event details with Pino's | Dinner Committee - Wine & Cheesecake | Nate Kean | Marty Golden | 2013-04-15 | Completed
Submit ad copy to office for publication in Kiruv, temple weekly phone blasts and bimah announcements; send e-blast with letter to listserv, post on Facebook/Twitter and repeat as needed in days prior to Yom HaShoah | Publicity - Wine & Cheesecake | Ray Sabin | Craig Artel | 2013-04-15 | Completed
Submit column for Kiruv - summer issue | Publicity | Craig Artel |  | 2013-05-03 | Completed
Reserve golf course | Activities - Golf Outing | Rich Zirin | Gene Gottlieb | 2013-05-13 | Completed
Secure participants | Activities - Golf Outing | Rich Zirin | Gene Gottlieb | 2013-05-27 | Completed
Send e-blast with letter to listserv, post on Facebook/Twitter and repeat as needed in days prior to event | Publicity - Golf Outing | Craig Artel | Rich Zirin | 2013-05-27 | Completed

## Sample
Sample Program Advanced Planning
Date
Task | Committee | Assignee | Assistant | Due Date | Status
Maintain chronology of events
Gather information about past presidents |  |  |  | 3.1.2013 | Done
Gather information about past Men of the Year | Man of the Year |  |  |  | Done
Member photographs (presidents, Men of the Year) |  |  |  | 3.15.2013 | Done
Event photographs (contact regional representatives) | Publicity |  |  | 3.15.2013 | Done
Softball team stats | Softball | Pete Schild |  | 3.1.2013 | Done
Upload scans of flyers and promotional material at least 2 weeks prior to event | Publicity |  |  | 3.25.2013 | Done
|  |  |  | 4.10.2013 | Done
|  |  |  | 4.15.2013 | Done
|  |  |  | 4.25.2013 | Done
Upload photos/graphics within 24 hours of event | Publicity |  |  | 4.30.2013 | Done
Upload Cake order forms and Wine lists at least 3 weeks prior to distribution | Cake & Wine Committee |  |  | 2.29.2013
Yom HaShoah candle delivery - Ask for volunteers | Yom HaShoah
yes
Lou