## Advanced Planning
Program Advanced Planning
Date
Task | Committee | Assignee | Assistant | Due Date | Status
.

## Sample
Program Advanced Planning - December to Remember
Date | Description
Nov | Representatives from Men's Club, Sisterhood, Chai Society discuss program and options for food and movies.
Nov | Finalize menu items and movies.
Nov | Submit online publicity form for internal publicity (Dave Diamond)
Nov | Complete program flyer and submit to temple (Dave Diamond)
Nov / Dec | Temple-wide publicity: announcement of program on Shabbat leaflets, program flyer around shul, standalone e-blasts about program, inclusion in weekly program announcements.
1-2 weeks prior to program | Secure all volunteers (10-15) on event date: arrange for food and supplies, drinks, set-up food, handle registration, verify room logistics, etc.
3 days prior to program | Expected number of attendees based on RSVPs to date and anticipated walk-ins (Joe Springut)
3 days prior to program | Submit room function form - Set-up for seating (tables + chairs), registration table, and tables for food and drinks, audio-visual needs for 2 simultaneous movies -TV, screen, projector, laptop, etc. (Jacob Kovel)
3 days prior to program | Arranage for all food, drinks, paper goods
Shortly after program | Work with Treasurer and Assistant Treasurer in determining all program revenues and expenses.