## Advanced Planning
Program Advanced Planning
Date
Task | Committee | Assignee | Assistant | Due Date | Status
.

## Sample
Program Advanced Planning - Faith and Destiny
Date | Description
2011-08-16 | Beth El member Annette Gavins reaches out to Men's Club board member Marty Melnick suggesting a temple-wide book review discussion. Agreement that Men's Club, Sisterhood, and Chai Society to collaborate together on a breakfast program.
2011-08-29 | "One book" program with local Rabbi Philip Lazowski, very well-known in the community. To be held on already scheduled Men's Club breakfast date, 3/18/12, and to coincide with packaging of Yellow Candles for Yom HaShoah. Program to include a discussion of Rabbi Lazowski's book "Faith and Destiny" and a documentary based on the book.
2011-09-08 | Confirmation from Rabbi Lazowski on his availability on 3/18/12.
2011-09-24 | First of five monthly articles written about program to be published in temple's November newsletter. Each subsequent article completed at least one month prior to publication of newsletter.
2011-11-21 | Request by Annette on information regarding: (1) charge for attendees, (2) who will take reservations, (3) publicity flyer, and (4) newspaper publicity.
2011-12-19 | Article being written for temple's February newsletter. Request by Annette that entire committee meets in February to discuss program logistics.
2011-12-27 | Program flyer completed by Dave Diamond.
January | Program detail provided to Carin Buckman, temple member in charge of marketing, for external publicity.
2012-02-12 | Committee meeting to discuss program logistics.
late Feb. | Temple-wide card mailed to all members about program.
late Feb. - mid-Mar. | Temple-wide publicity: announcement of program on Shabbat leaflets, program flyer around shul, standalone e-blasts about program, inclusion in weekly program announcements.
2012-03-15 | Key program items: (a) Expected # of attendees based on RSVPs to date and estimated walk-ins; (b) room set-up function form; (c ) Books for sale - Both "Faith and Destiny" and two other books written by Rabbi Lazowski" - profits to go to charity; (d) Items as door prizes to offset program costs: we have 5 items - an afghan, a shawl, a hat/scarf combo ( these 3 items are hand made ), a beautiful Jewish calendar and a great thermos bottle - tickets: 1 for $5 or 3 for $10; (e) breakfast food/drinks handled by Men's Club; (f) registration, set-up, and helping to serve food; (g) audio-visual needs, eg, TV to show documentary.
late March | Discuss final accounting of program revenues and expenses; and allocate between sponsoring temple arms.