## Advanced Planning
Program Advanced Planning
Date
Task | Committee | Assignee | Assistant | Due Date | Status
.

## Sample
Program Advanced Planning - Succahfest in the Sukkah
Date | Description
May / June | Secure date for Succahfest in the Succah with the temple programming director.
July / August | Submit online publicity form for internal publicity (Dave Diamond)
July / August | Complete program flyer and submit to temple (Dave Diamond)
September | Assemble trivia contest with Q + A (Dave Diamond)
Sept / October | Temple-wide publicity: announcement of program on Shabbat leaflets, program flyer around shul, standalone e-blasts about program, inclusion in weekly program announcements.
1-2 weeks prior to program | Secure Men's Club volunteers (3-4) on event date: pick-up all food/drinks and supplies, handle registration, verify room logistics, etc.
3 days prior to program | Expected number of attendees based on RSVPs to date and anticipated walk-ins (Joe Springut)
3 days prior to program | Submit room function form - Set-up for seating (tables + chairs), registration table, and tables for food and drinks, podium/mic if needed, and any audio-visual needs -TV, screen, projector, laptop, etc. (Dave Diamond)
3 days prior to program | Arranage for all food, drinks, paper goods (Joe Springut / Jacob Kovel)
Shortly after program | Work with Treasurer and Assistant Treasurer in determining all program revenues and expenses.