## Explanation
Torch Award Program Schedule
On the online application, we ask that you describe the timeline with all the tasks to make the program work. The timeline will explain: aspects of program advance planning, how long did it take, key events, how did your members participate. Describe this information on a spreadsheet such as the ones that follow and upload it to the online application.

## Sample 1
Torch Award Program Schedule |  |  | (Sample items inserted)
As of Date
2020-06-06
Task |  | Assignee | Assistant | Due Date | Status
Planning
Update email list for latest committee (remove old members) |  | Jim |  | 2020-03-01 | Done
Add new committee member or two |  | Robert | Brian | 2020-03-01 | Done
Create budget | Finance | Bruce |  |  | Done
Book Room |  | Bruce |  | 2020-03-01 | Done
Speaker Topics | Speakers | Joe | Jim | 2020-03-15 | Done
Update menus | Commisary | Jim |  | 2020-04-25 | Done
Publicity
Update website |  | Jacob |  | 2020-03-01 | Done
Email Save-the-Date to Temple Bulletins |  | Jacob |  | 2020-03-15 | Done
Produce brochure or flyer | Publicity | Josh | Jim | 2020-03-25 | Done
Phone-a-thon |  | Robert | Brian | 2020-03-28 | Open
Create press releases; articles | Publicity | Josh | Jim | 2020-04-10 | Done
Email press releases to newspapers |  | Josh |  | 2020-04-15 | Done
Get photographer |  | Joe |  | 2020-04-30 | Done
Execution
Purchase menu items |  | Jim |  | 2020-06-01 | Done
Room set up |  | Bruce |  | 2020-06-03 | Done
Set out food |  | Jim |  | 2020-06-08
Welcome speaker |  | Joe |  | 2020-06-08
Welcome attendees |  | Josh | Robert | 2020-06-08
Lessons Learned Meeting |  | all |  | 2020-06-15

## Sample 2
Torch Award Program Schedule |  |  | (Sample items inserted)
As of Date
2020-06-06
Task |  | Assignee | Assistant | Due Date | Status
Update email list for latest committee (remove old members) |  | Jim |  | 2020-03-01 | Done
Add new committee member or two |  | Robert | Brian | 2020-03-01 | Done
Create budget | Finance | Sam |  | 2019-08-01 | Done
D'var Torah | Speakers | Jeremey |  | 2020-03-15 | Done
Email Save-the-Date to Temple Bulletins |  | Sam |  | 2019-07-15 | Done
Phone Calls |  | Tyler |  | 2019-08-01 | Done
Produce Flyer | Publicity | Sam |  | 2019-07-24 | Done
Create RSVP form | Publicity | Sam |  | 2019-07-24 | Done
Done
Update menus | Commisary | Sam |  | 2020-04-25 | Done
Create Seating Plan |  | Joe |  | 2020-04-30 | Done
Phone Calls to all members |  | Tyler |  | 2019-08-01 | Open
Book Room |  | Bruce |  | 2020-03-01 | Done
Lessons Learned Meeting |  | all |  | 2020-06-15