## Advanced Planning
Program Advanced Planning
Date
Task | Committee | Assignee | Assistant | Due Date | Status
Contact Speaker | Clergy | Rabbi Goldman | Dan Hammer | 2/1/12 | Done
Arrange Travel | Brotherhood | Dan Hammer | N/A | 2/15/12 | Done
Budget | Brotherhood | Richard Freiberg | N/A | 2/15/12 | Done
Arrange Weekend Agenda | Clergy | Rabbis Goldman & Tucker | Rabbis Goldman & Tucker | 4/1/12 | Done
Arrange Publicity - Synagogue | Brotherhood | Richard Freiberg | Caroline Geller | 4/1/12 | Done
Brotherhood Publicity | Brotherhood | Richard Freiberg | Dan Hammer | 4/1/12 | Done
Arrange Logistics | Brotherhood | Rob LeBoyer | Mel Lipetz | 4/1/12 | Done
Arrange Food | Brotherhood | Rob LeBoyer | Mel Lipetz | 4/1/12 | Done
Recap | Brotherhood | Richard Freiberg | Brotherhood | 5/15/12 | Done
.