## Advanced Planning
Program Advanced Planning
Date
Task | Committee | Assignee | Assistant | Due Date | Status
Contact Speaker | Speaker Comm | Cliff Rothman | Jack Pollowitz | 9/1/12 | Done
Budget | Brotherhood | Richard Freiberg | Robert LeBoyer | 9/1/12 | Done
Arrange Agenda | Speaker Comm | Sam Fredman | Harold Nissen | 10/1/12 | Done
Arrange Publicity - Synagogue | Brotherhood | Richard Freiberg | Caroline Geller | 10/1/12 | Done
Arrange Newspaper Publicity | Speaker Comm | Jack Pollowitz | N/A | 10/1/12 | Done
Bulletin Bios | Speaker Comm | Cliff Rothman | Jack Pollowitz | 10/1/12 | Done
Brotherhood Publicity | Brotherhood | Richard Freiberg | Dan Hammer | 10/1/12 | Done
Arrange Logistics | Brotherhood | Rob LeBoyer | Mel Lipetz | 10/22/12 | Done
Arrange Food | Brotherhood | Rob LeBoyer | Mel Lipetz | 10/22/12 | Done
Recap | Brotherhood | Richard Freiberg | Brotherhood | 10/22/12 | Done
.